## Implementation Tracker
Phase | Ref | Task Name | What Changes | Why | Type | Files Affected | Dependencies | Status | Status (updated 2026-04-14)
0 | 0.1 | Save transcript to lead | After Claude analysis, write transcript_text to lead record if lead_id known | Transcripts are lost after analysis. No history for progressive intelligence. | Fix | routes/recommendation/index.ts | None | TRUE
0 | 0.2 | Extract service functions | Create intelligenceService.ts, beliefAnalysisService.ts, analysisPipeline.ts. Refactor route handlers to thin wrappers. | Logic trapped in route handlers can't be called from webhooks, queue, or other routes. | Service | lib/intelligenceService.ts, lib/beliefAnalysisService.ts, lib/analysisPipeline.ts, routes/lead-intelligence, routes/lead-beliefs | None | TRUE
0 | 0.3 | Intelligence: merge not overwrite | Pass existing intelligence profile as context to Claude. Add preserve/merge instructions. | Each call overwrites previous profile. Hot button from call 1 wiped by call 2. | Service | lib/intelligenceService.ts | 0.2 | TRUE
0 | 0.4 | Belief analysis: preserve established | Pass existing belief states as context. ESTABLISHED stays unless explicit reversal. | Beliefs established in call 1 reset to UNKNOWN in call 2 because not discussed. | Service | lib/beliefAnalysisService.ts | 0.2 | TRUE
0 | 0.5 | Auto-trigger pipeline | After /recommendation/analyze, fire runPostTranscriptPipeline() in background if lead_id provided. | Users must manually click Generate Profile then Analyze Beliefs. 3 clicks instead of 0. | Service | routes/recommendation/index.ts, lib/analysisPipeline.ts | 0.1, 0.2 | TRUE
0 | 0.6 | Fix feature-update dry_run | Add conditional skip of DB writes when dry_run: true. | dry_run parameter accepted but ignored. Testing corrupts document review states. | Fix | routes/content/feature-update.ts | None | TRUE | Was already implemented correctly in code
0 | 0.7 | Server-side pagination | Add page/page_size params, LIMIT/OFFSET, COUNT(*). Frontend page controls + debounced search. | GET /leads returns all leads. Won't work with 25K+. | Route + Frontend | routes/leads/index.ts, pages/leads.tsx, openapi.yaml, api-zod | None | TRUE | Backend code done, frontend compatibility fix applied. Build/bundle issue under investigation.
0 | 0.8 | Schema: leads table additions | Add email, phone, call_attempts, last_call_outcome, callback_date, outreach_paused_until, batch_date, campaign_name, sequence_stage, pipedrive_person_id | Pipedrive sync, Aircall matching, and call outcome logic all need these fields. | Schema | lib/db/src/schema/leads.ts | None | TRUE | Schema pushed, columns verified in DB
0 | 0.9 | Schema: belief registry questions | Add conversation_question, content_if_unresolved, red_flag_signals, green_flag_signals. Seed data for all 16+ beliefs. | Call prep page needs to show what question to ask per belief and what content to send. | Schema + Config | lib/db/src/schema/belief-registry.ts, dataManager.ts | None | TRUE | Schema pushed, seed data migrated via SQL script
0 | 0.10 | Schema: lead_conversations table | Generic conversations table replacing Aircall-specific. Source field (aircall/fireflies/manual). beliefs_before/after snapshots, intelligence_delta. | Transcripts come from multiple sources. Pipeline doesn't care about source. | Schema | lib/db/src/schema/lead-conversations.ts, lib/db/src/schema/index.ts | None | TRUE | Schema pushed, table verified in DB
0 | 0.11 | Conversation summary generation | After analysis, Claude generates 3-5 sentence summary. Future analyses receive summaries as context. | Progressive intelligence needs summaries. Full transcripts won't fit in context. | Service | lib/analysisPipeline.ts | 0.2, 0.10 | TRUE
1 | 1.1 | Contact pool schema | Create contacts table: name, email, phone, company, source_list, upload_batch, dedup_status, campaign_name, dispatch_status (pool/queued/dispatched/called/qualified/archived), dispatch_date, call_attempts, last_call_outcome, callback_date, outreach_paused_until, cool_off_until, aircall_contact_id, pipedrive_person_id, pipedrive_deal_id, lead_id (FK to leads, nullable), created_at, updated_at. Also add contact_id (FK to contacts) on leads table. | App is the master record for all contacts. 25K+ contacts uploaded via CSV. Aircall and Pipedrive IDs are null until pushed. | Schema | lib/db/src/schema/contacts.ts, lib/db/src/schema/leads.ts, lib/db/src/schema/index.ts | None | FALSE | v6: App owns data. Bidirectional FK between contacts and leads.
1 | 1.2 | Data ingestion UI + service | Upload CSV/Excel. Column mapping interface. Normalisation (phone E.164, email validation, name cleaning). Dedup hierarchy: 1) exact email match, 2) normalised phone match, 3) fuzzy name+company. Preview shows: X new, Y exact dupes (skip), Z possible matches (user chooses merge/skip/update). Update option refreshes contact details from newer CSV. Store upload history with source_list and date. | Data enters via CSV upload to the app, not from Pipedrive. Bad dedup means duplicate contacts in Aircall and wasted dials. | Service + Frontend | lib/contactIngestionService.ts, routes/contacts/index.ts, pages/contact-ingestion.tsx | 1.1 | FALSE | Dedup hierarchy defined. User chooses merge/skip/update for fuzzy matches.
1 | 1.3 | Aircall API client (contacts) | Create lib/integrations/aircall/client.ts: createContact(firstName, lastName, phone, email), getContact(id), listUsers(). Create contact in Aircall when queued for calling, store aircall_contact_id on contact record. No power dialer functions. | Need contacts to exist in Aircall before calling so webhook events match back. Click-to-call replaces power dialer — simpler, caller controls pace. | Integration | lib/integrations/aircall/src/client.ts | 2.0a | FALSE | Rate limit: 60 req/min. Contact created on queue, not on upload.
1 | 1.4 | Campaign config + local queue service | Campaigns: name, filter criteria on local contact pool, daily_quota, assigned agent. Queue service: query contacts matching criteria, exclude dispatched/cool-off/no-interest, mark as queued with dispatch_date, create contact in Aircall if aircall_contact_id is null. Start-of-day reconciliation: queued contacts with no call record from yesterday reset to pool. No Aircall power dialer — queue is managed locally. | Daily call queue managed in our app. Contacts pushed to Aircall on queue so they exist for matching. Caller uses click-to-call from our UI. | Service + Schema | lib/db/src/schema/campaign-config.ts, lib/dispatchService.ts, routes/campaigns/index.ts | 1.1, 1.3 | FALSE | Local queue replaces Aircall power dialer.
1 | 1.5 | Campaign Config + Call Queue page | Campaign config: create/edit campaigns, filter criteria on local pool, assign agent, set daily quota. Call Queue view: today's prioritised list (callbacks, interested, retries, fresh). Each row shows contact name, company, phone, last outcome, call attempts. Click-to-call button per row (triggers aircall:// protocol or embedded widget). Fill Queue button with breakdown. Embedded Aircall phone widget in side panel for side-by-side calling. | Caller opens one page each morning, sees their queue, clicks Call — Aircall opens alongside lead context. No app switching. Tags and notes captured in Aircall widget, flow back via webhooks. | Frontend | pages/campaign-config.tsx, pages/call-queue.tsx, components/aircall-widget.tsx, components/layout.tsx, App.tsx | 1.4, 2.0a | FALSE | Aircall Phone SDK embedded widget. Click-to-call for outbound.
1 | 1.6 | Pipedrive push service | One-way push on interested/meeting-booked outcomes. Create person + deal in Pipedrive. Store pipedrive_person_id and pipedrive_deal_id on contact record. No sync, no cache, no Pipedrive webhooks. | Only qualified leads enter Pipedrive. Keeps it clean. App remains source of truth. | Service | lib/pipedrivePushService.ts, routes/pipedrive/index.ts | 1.1 | FALSE | Simple one-way push, not bidirectional sync.
1 | 1.7 | Aircall embedded phone widget | Integrate Aircall Phone SDK as embeddable widget. Side panel component that can be toggled open/closed. Supports make/receive calls, tagging, notes, after-call work — all within our app. Widget state syncs with current contact being viewed. | Eliminates app switching between Aircall and Content Unlocker. Caller sees belief map and context while on the call. Tags captured in widget flow back via webhooks. | Frontend + Integration | components/aircall-widget.tsx, pages/call-queue.tsx, pages/call-prep.tsx | 2.0a | FALSE | Requires Aircall Phone SDK. Research embed options.
2 | 2.0a | Integration settings schema | Create integration_configs table: id, provider (aircall/pipedrive/fireflies/google_calendar), config (JSONB — credentials, webhook URL, settings), enabled (boolean), created_at, updated_at. Create agents table: id, name, email, aircall_user_id, active, created_at. | Need persistent storage for API credentials, webhook tokens, and agent mappings. Currently only env vars which require redeploy to change. | Schema | lib/db/src/schema/integration-configs.ts, lib/db/src/schema/agents.ts, lib/db/src/schema/index.ts | None | TRUE | Config JSONB structure varies by provider
2 | 2.0b | Integration settings API routes | CRUD routes: GET/POST/PATCH /settings/integrations/:provider. GET /settings/agents, POST /settings/agents, PATCH /settings/agents/:id. POST /settings/integrations/aircall/test-connection (validates credentials). POST /settings/integrations/aircall/register-webhook (registers webhook URL with Aircall API). GET /settings/integrations/aircall/users (fetches available users from Aircall API). | Frontend needs endpoints to manage credentials, test connections, register webhooks, and manage agents. | Route | routes/settings/index.ts, routes/index.ts | 2.0a | TRUE | Credentials stored encrypted or at minimum not returned in full via GET
2 | 2.0c | Integration settings page | New Settings page with provider tabs. Aircall tab: API ID/Token fields, webhook URL display with copy button, Test Connection button with status indicator, transcription mode toggle (AI Assist / External). Agent Management section: list agents with Aircall user mapping, add/remove agents, fetch users from Aircall. Placeholder tabs for Pipedrive, Fireflies, Google Calendar. | Team needs to configure integrations without code changes or redeployment. Agent mapping needed for call attribution. | Frontend | pages/settings.tsx, components/layout.tsx, App.tsx | 2.0b | TRUE | Extends existing settings icon in top nav
2 | 2.1 | Aircall: design constraints (research) | Document Aircall API behavior: no transcript in call.ended, tags arrive late, transcription needs AI Assist. | Must understand API before building. Wrong assumptions = broken integration. | Config | N/A (documented in plan) | None | TRUE | Done — ADR 001 canonical tag model + webhook handler + constraints documented
2 | 2.2 | Aircall: transcription service | Two paths: AI Assist (webhook) or external (download MP3 + Whisper/Deepgram). Config-driven. | call.ended has no transcript. Must handle transcription separately. | Service | lib/transcriptionService.ts | 0.10 | TRUE | Done — transcription.created handler with AI Assist + utterance parser
2 | 2.3 | Aircall: extract transcript utils | Move isAircallFormat, normaliseAircallTranscript, identifyAgentLabel to shared utility. | These functions are embedded in recommendation route. Need them in webhook handler too. | Utility | lib/aircallTranscriptUtils.ts, routes/recommendation/index.ts | None | TRUE | Done — transcription parser in aircall/index.ts (utterances → Agent:/Contact: lines)
2 | 2.4 | Aircall: call outcome service | Map tags to actions. TAG_MAPPING config object. interested/no-interest/meeting-booked/no-answer/callback/not-now. | Without outcomes, leads stay in same state regardless of call result. Loop doesn't close. | Service | lib/callOutcomeService.ts | 0.8, 0.10 | TRUE | Done — applyTagOutcome with full canonical outcome + side-effect model
2 | 2.5 | Aircall: webhook handler | POST /aircall/webhook handling call.ended, call.tagged, transcription.created events. | Need to receive Aircall events automatically instead of manual file upload. | Route | routes/aircall/index.ts, routes/index.ts | 2.2, 2.3, 2.4 | TRUE | Done — full webhook handler: call.ended / call.tagged / call.commented / transcription.created / summary.created + SSE broadcast
2 | 2.6 | Fireflies: webhook handler | POST /fireflies/webhook. Match by participant email. Create lead_conversations, trigger pipeline. | Google Meet transcripts must flow automatically. Manual paste = inconsistent logging. | Route | routes/fireflies/index.ts, routes/index.ts | 0.10, 0.5 | FALSE | Env: FIREFLIES_WEBHOOK_SECRET
2 | 2.7a | Google Calendar: API client | Create lib/integrations/google-calendar/ with OAuth flow, event CRUD, date range queries. | Need Calendar API access for meeting and callback invites. | Integration | lib/integrations/google-calendar/src/client.ts | None | FALSE | Env: GOOGLE_CALENDAR_CLIENT_ID/SECRET/REDIRECT
2 | 2.7b | Google Calendar: calendar service | createMeetingEvent, createCallbackEvent, createFollowUpEvent, getEventsForDate. | Outcome dialog needs to auto-create calendar events for meetings and callbacks. | Service | lib/calendarService.ts | 2.7a | FALSE
2 | 2.7c | Google Calendar: outcome dialog | Add date/time picker to outcome dialog. Auto-create calendar event for meeting-booked and callback-requested. | Investors need calendar invites. No invite = nothing in their diary. | Frontend | pages/call-prep.tsx, pages/call-inbox.tsx | 2.7b, 2.4 | FALSE
2 | 2.8a | Frontend: Call Inbox page | New page listing all conversations. Source icons, status indicators, filters, manual link, reprocess. | Need visibility of all calls/meetings across sources with status tracking. | Frontend | pages/call-inbox.tsx, components/layout.tsx, App.tsx | 2.5, 2.6 | FALSE
2 | 2.8b | Frontend: Lead detail updates | Add Log Meeting button, Conversations section with summaries, belief diffs, intelligence delta. | Lead detail needs conversation history and what-changed views. | Frontend | pages/lead-detail.tsx | 0.10, 0.11 | FALSE
3 | 3.1 | Pipeline: job tracking schema | pipeline_jobs table with batch_id, job_type, status, lead_id, attempts, timestamps. | Need persistent job tracking for batch processing. | Schema | lib/db/src/schema/pipeline-jobs.ts | None | FALSE
3 | 3.2 | Pipeline: queue service + orphan recovery | pipelineQueue.ts using batchProcess utility. Startup recovery, 60s polling, heartbeat. | Replit may kill processes mid-batch. Must detect and recover orphaned jobs. | Service | lib/pipelineQueue.ts | 3.1, 0.2 | FALSE
3 | 3.3 | Pipeline: API routes + frontend | POST /enqueue, GET /status, GET /jobs. Bulk Run Pipeline actions on leads + contact pool. Progress banner. | Need to enqueue hundreds of leads and track progress. | Route + Frontend | routes/pipeline/index.ts, pages/leads.tsx, pages/contact-pool.tsx | 3.2, 0.7 | FALSE
4 | 4.1 | Belief-driven call prep page | Complete redesign: qualification gates, belief map with questions, context (summaries, sent docs, objections), action buttons. | Caller needs belief map as primary interface before every call. Current page is generic 4 questions. | Frontend | pages/call-prep.tsx, routes/leads/index.ts (call-prep endpoint) | 0.9, 0.10, 0.11 | FALSE | THE primary interface
4 | 4.2 | Daily call queue page | New page: prioritised list (callbacks, interested, cold at sequence day, re-entries). Re-entry reset at query time. | Caller needs to know who to call each morning. Currently no prioritised list. | Frontend + Route | pages/call-queue.tsx, routes/leads/index.ts (call-queue endpoint) | 2.4, 0.8 | FALSE | Re-entry flips paused->active at query time
4 | 4.3 | Dashboard: campaign wave tracking | Widget showing active wave, dispatched today/week, total in wave, remaining in pool. | Team needs to see where they are in the 25K campaign. | Frontend + Route | pages/dashboard.tsx, routes/dashboard/index.ts | 0.8 | FALSE
4 | 4.4 | Dashboard: funnel view | Counts by pipeline_stage. Plus terminal states (Closed, Paused, Passive). | Need 'where is everyone right now' at a glance. | Frontend + Route | pages/dashboard.tsx, routes/dashboard/index.ts | 0.8 | FALSE
4 | 4.5 | Dashboard: error visibility | 'X items need attention' widget. Failed jobs, syncs, unmatched calls, unprocessed outcomes. | Silent failures where leads fall through cracks is worst outcome. | Frontend + Route | pages/dashboard.tsx, routes/dashboard/index.ts | 2.5, 3.1 | FALSE
4 | 4.6 | Enhanced lead detail timeline | Unified timeline: stage changes, conversations, sends, belief transitions, intelligence updates. | Need complete chronological interaction history per lead. | Frontend | pages/lead-detail.tsx | 0.10, 2.4 | FALSE
4 | 4.7 | Content routing audit | Review recommendation route. Ensure belief gates are primary driver, stage is sanity check only. | Stage currently filters content alongside beliefs. Beliefs should be primary. | Review + Fix | routes/recommendation/index.ts | None | FALSE | Review task, not rewrite
4 | 4.8 | Belief system admin page | New page: belief registry editor, document-to-belief matrix, gate rules overview. | Non-developers can't adjust beliefs, questions, gates, or content mappings without code. | Frontend | pages/belief-admin.tsx, components/layout.tsx, App.tsx | 0.9 | FALSE
4 | 4.9 | Content handoff | Copy to Clipboard for AC paste. Better send history UI. Outreach queue page (optional). | Content goes to AC manually. Need smooth copy flow. | Frontend | pages/lead-detail.tsx, pages/recommend.tsx | None | FALSE | Outreach queue deferred unless >50/day
S | S1 | Discovery completeness score | Score each conversation 0-100% on new intelligence gathered. Aggregate per agent. | See which callers do real discovery vs going through motions. | Service + Frontend | lib/analysisPipeline.ts, pages/call-inbox.tsx | 0.2, 0.11 | FALSE | Post-core
S | S2 | Belief journey analytics | Dashboard: hardest beliefs, avg conversations per belief, distribution by cluster. | Identify systematic weaknesses in scripts or content. | Frontend + Route | pages/dashboard.tsx or new analytics page | 0.10 | FALSE | Post-core
S | S3 | Content effectiveness tracking | Link doc sends to subsequent belief state changes. Build effectiveness map. | Data-driven content strategy. Rewrite underperforming documents. | Service + Frontend | lib/analysisPipeline.ts, pages/dashboard.tsx | 0.10, 0.11 | FALSE | Post-core
S | S4 | Objection memory | Track objections across conversations with resolution status. Show in call prep. | Callers don't re-raise resolved objections. Surface recurring issues. | Schema + Service | lib/db schema changes, lib/analysisPipeline.ts, pages/call-prep.tsx | 0.10, 4.1 | FALSE | Post-core
S | S5 | Smart next action engine | Multi-step: conversational goal + content + gate check + escalation trigger. | From 'what to send' to 'what to do next and why'. | Service | routes/leads/index.ts, lib/analysisPipeline.ts | 0.9, 4.1 | FALSE | Post-core
S | S6 | Pre-call briefing card | Claude auto-generates 30-second context briefing per lead. Cached, regenerated after each call. | Perfect context in 30 seconds before every call. | Service + Frontend | routes/leads/index.ts, pages/call-prep.tsx | 0.2, 0.11, 4.1 | FALSE | Post-core
S | S7 | Belief-based lead scoring | Score based on qualification gates, universal/cluster/founding beliefs. Formula-driven. | Prioritise genuinely ready leads over email openers. | Service + Frontend | routes/leads/index.ts, pages/leads.tsx, pages/call-queue.tsx | 0.9 | FALSE | Post-core
CL | CL.1 | Contacts + pool schema | Contacts table with dispatch_status (pool/dispatched/called/archived), dispatch_date, call_attempts, last_call_outcome, callback_date, cool_off_until | Operator needs to track which prospects are in active call lists, which are cooling off, which have been called N times | Schema | lib/db/src/schema/contacts.ts | None | TRUE | campaign_name column removed in the v2 membership refactor
CL | CL.2 | Call list configs schema | call_list_configs table with name, daily_quota, assigned_agent_id, active, filter_criteria (source_lists, exclude_outcomes), total_dispatched/called/qualified stats | Operator creates named call lists with per-list quota and filter rules | Schema | lib/db/src/schema/call-list-config.ts | CL.1 | TRUE
CL | CL.3 | Call list memberships bridging table | call_list_memberships with (call_list_id, contact_id, added_at, removed_at, removal_reason, outcome_at_removal, carried_from_id). Partial unique index enforces one active membership per contact. | Append-only audit trail of which contacts were on which lists, when, why they left. Enables proper carry-over semantics and recall chains. | Schema | lib/db/src/schema/call-list-memberships.ts | CL.1, CL.2 | TRUE
CL | CL.4 | Dispatch service | fillQueue + getQueueStatus + getCallList + reconcileUncalledContacts with 4 priority buckets (callbacks, interested, retries, fresh) + tier 5 for immediate_recall + callback_date filter + configurable max_call_attempts | Drives every-day queue composition deterministically from contact state | Service | artifacts/api-server/src/lib/dispatchService.ts | CL.1-3 | TRUE
CL | CL.5 | Campaigns-dispatch API routes | CRUD for call lists + queue status + fill-queue + carry-over + reconcile + pool-count + call-list. Carry-over creates new membership on target list with carried_from_id. | Frontend operator actions | Routes | artifacts/api-server/src/routes/campaigns-dispatch/index.ts | CL.4 | TRUE
CL | CL.6 | Call Command page | Call Command page: queue composition, current contact card with Load Call button, Up Next list (clickable rows swap positions), Previous/Next navigation, stale-contact banner, auto-polling | Operator's day-to-day dialing UI | Page | artifacts/unlock-intel/src/pages/call-command.tsx | CL.5 | TRUE
CL | CL.7 | CSV upload to pool | Upload contacts to the pool via CSV with dedup + batch tracking | Initial data ingestion | Page + Service | artifacts/unlock-intel/src/pages/contacts-upload.tsx (check) | CL.1 | TRUE | Existing before this tracking period
AC | AC.1 | Agents table + API | agents table linking our operator records to Aircall user_ids | Webhook agent filter — only our agents' calls are processed | Schema + Routes | lib/db/src/schema/agents.ts, routes/settings/index.ts | None | TRUE
AC | AC.2 | Canonical tag/outcome/side-effect model | 8 outcomes × 9 side-effects with allowed-combinations matrix. Dumb tags (record_only + unmapped auto-record). Default mapping for Tom's live Aircall tags. | Deterministic, configurable mapping from Aircall tags to contact outcomes. See ADR 001. | Service | artifacts/api-server/src/lib/tagModel.ts | None | TRUE
AC | AC.3 | Per-tag + global cool_off_days | Cool-off period configurable globally and per-tag. UI input in Settings. | Different tags warrant different cool-off periods (Hung Up vs Not Interested) | Service + UI | artifacts/api-server/src/lib/tagModel.ts, routes/aircall, settings page | AC.2 | TRUE
AC | AC.4 | Configurable max_call_attempts | Max attempts stored in integration_configs.config (default 3, range 1-20). Applied to retry bucket. | Different campaigns need different tolerance for persistence | Service + UI | lib/dispatchService.ts, settings page | CL.4 | TRUE
AC | AC.5 | Webhook single-mutation-point refactor | call.ended is now informational only. call.tagged is the SOLE state-mutation point — all changes happen in a Drizzle transaction. Eliminates race conditions. | Aircall webhook ordering is not guaranteed; concurrent processing caused data corruption (missing recalls, wrong dispatch_status). | Service | artifacts/api-server/src/routes/aircall/index.ts | AC.2 | TRUE
AC | AC.6 | Untagged-conversation sweep | Background sweep every 5 min closes conversations that have call.ended but no call.tagged after 10 min. Treats as 'untagged'. | Safety net for rare case where Aircall never delivers the tag webhook. | Service | artifacts/api-server/src/routes/aircall/index.ts | AC.5 | TRUE
AC | AC.7 | SSE live queue updates | /api/events/queue long-lived Server-Sent Events stream. Webhook handlers + sweep push events; frontend EventSource refreshes instantly. | Replaces polling burst. Reliable refresh even for slow taggers. | Service + Integration | artifacts/api-server/src/lib/queueEvents.ts, routes/events, call-command.tsx | AC.5 | TRUE
AC | AC.8 | Credential overwrite bug fix | Settings no longer overwrites API token with masked placeholder on save. Backend strips any field value starting with '****' on save. Frontend doesn't pre-fill password inputs. | Every Settings save was silently corrupting the API token — the 'Aircall keeps breaking' pattern. | Fix | routes/settings/index.ts, pages/settings.tsx | None | TRUE
AC | AC.9 | Diagnostic error surfaces | Aircall API errors surface full HTTP status + body snippet + key prefix + actionable hint (401/403/429/5xx) | Enables rapid diagnosis without log hunting | Fix | routes/settings/index.ts, pages/settings.tsx | None | TRUE
E | E.1 | Phase 1 — Engine core (V2) | Pure module: config (A1-A9) + types + 10 functions (C1-C10) + 16 test fixtures. Spec 402_V2. Version 2.0.0. processTranscript returns EngineOutput. | Deterministic pattern-based engine replaces brittle LLM scoring. Config-driven so spec updates are mechanical. | Engine | artifacts/api-server/src/engine/v2/** (config, types, functions/*, tests/*, version) | None | TRUE | All 16 fixtures passing
E | E.2 | Phase 2 — Persistence | 5 new tables: engine_investor_state, engine_signals, engine_signal_transitions, engine_runs, engine_artifacts_sent. Plus engine_version column on lead_conversations. loadInvestor / saveEngineRun service. | Engine output persisted with full audit trail per contact | Schema + Service | lib/db/src/schema/engine-*, engine/v2/persistence.ts | E.1 | TRUE
E | E.3 | Phase 3 — Transcript wiring | handleTranscriptionCreated runs engine after storing transcript. Inspection endpoints: /engine/version, /engine/contact/:id, /engine/runs/:id, POST /engine/reprocess. | Automatic engine runs on every transcript; backfill endpoint for pre-existing transcripts | Routes + Integration | routes/aircall/index.ts, routes/engine/index.ts | E.1, E.2, AC.5 | TRUE
E | E.4 | Phase 4 — Outcome Drawer | Right-side slide-out on Call Command. Shows persona, hot button, signal changes, NBA card with document + cover note preview, gates, flags, fact find, previous runs history. Polls while waiting for engine run. | Operator sees immediate outcome + next-action recommendation after each call | Component + Page | artifacts/unlock-intel/src/components/OutcomeDrawer.tsx, call-command.tsx | E.3 | TRUE | [Send] disabled until Phase 8 (Pipedrive)
E | E.5 | Phase 4.5 — V3 engine upgrade | Add config sections A10-A17 (Question Registry, Demo Segment Map, Cold Call Script, Email Templates, Problem Belief Patterns, Post-Close Workflow, Adviser Loop, Book 2 Routing). New functions C11-C16. EngineOutputV3 shape (backwards-compatible superset). Fixtures D6-D9. Bump version to 3.0.0. | Close 7 gaps identified in V3 spec: structured question detection, demo segment tracking, email generation, post-close workflows, adviser loop, Book 2 routing | Engine | artifacts/api-server/src/engine/v2/** (will be renamed to v3 or kept as v2 module with V3 version) | E.3 | FALSE | See docs/402_SPEC_Intelligence_Engine_V3_CURRENT.md. ~90% additive.
E | E.6 | Phase 4.6 — Outcome Drawer V3 fields | Extend drawer to show: Questions detected (+ undetected warnings), demo segment coverage (+ C4 gate violations), email draft preview (replaces cover-note-only display), post-close checklist, adviser-loop checklist, Book 2 routing badge | Surface V3 engine output in the operator UI | Component | artifacts/unlock-intel/src/components/OutcomeDrawer.tsx | E.5, E.4 | FALSE
E | E.7 | Phase 5 — Pre-call Intelligence Panel | Replaces empty Call Prep card on Call Command. Persona badge + confidence, hot button, profile summary, prior-call count, last outcome. With V3: 'questions to ask on this call' (filtered by signal states) + demo segment map for next call. | Operator has context on current contact before dialing | Component + Page | call-command.tsx, new component | E.3, E.5 | FALSE
E | E.8 | Phase 6 — V1 migration + retirement | Map old lead_beliefs enum to V2 states and copy into engine_signals. Deprecate beliefAnalysisService, intelligenceService, analysisPipeline. Retire or rebuild old Beliefs tab on lead-detail.tsx. | Remove duplicated intelligence system once V2/V3 has proven out | Migration | Migration script + delete old services | E.7 | FALSE | Only after V2/V3 runs have built up enough confidence
E | E.9 | Phase 7 — Engine update mechanism | Admin page listing current signals/gates/routing with last-updated timestamps. /engine/version endpoint already exists. Document CONFIG_ONLY / ADDITIVE / BREAKING update workflow for future V4/V5 spec drops. | Future spec updates should be mechanical, not require re-reading the whole engine | UI + Docs | New admin page + doc | E.5 | FALSE
PD | PD.1 | Disable Aircall's native Pipedrive integration | Go-live checklist item: turn off Pipedrive call-logging in Aircall dashboard. Verify no Activities appear for test calls until our adapter fires. | Native integration syncs EVERY call with no filtering — would dump prospecting noise into Pipedrive and duplicate our Activities. | Config | Aircall dashboard (no code) | None | FALSE | Decision documented in ADR 002
PD | PD.2 | Pipedrive adapter service | Single module with narrow methods: findOrCreatePerson, findOrCreateDeal, updateDealStage, sendEmail (headless via Pipedrive mailbox), createActivity, upsertCustomFields, closeDeal, logNote | Our app is the brain; Pipedrive is the execution substrate (email, deal board, timeline). All writes go through one module. | Service | artifacts/api-server/src/lib/pipedriveAdapter.ts (new) | None | FALSE | See ADR 002
PD | PD.3 | Document registry | Table linking our doc_id to pipedrive_file_id (docs uploaded once into Pipedrive Files). Engine recommends doc 140 → adapter attaches pipedrive_file_id=123457. | Pattern A from ADR 002 — files live in Pipedrive, our DB holds the mapping | Schema | New schema table | PD.2 | FALSE
PD | PD.4 | Pipedrive webhook dead-letter queue | New pipedrive_webhook_events table (status/attempts/last_error). Persist payload first, process second. Signature verification required. Retry backoff: 1m/5m/15m/1h/give up after 5. | Pipedrive webhook delivery can fail — must not silently lose events | Schema + Service | New schema + retry worker | PD.2 | FALSE
PD | PD.5 | Pipedrive audit log | pipedrive_audit_log table: every outbound push with timestamp, entity, action, pipedrive_id, success, duration. 90-day retention minimum. | Indispensable for troubleshooting integration issues | Schema | New schema | PD.2 | FALSE
PD | PD.6 | Rate limiter + backoff | Token-bucket limiter shared across all adapter calls. Exponential backoff on 429. Retry with jitter on 5xx. Background jobs at lower priority. | Pipedrive has per-token rate limits; must not burst-limit during normal operation | Service | Adapter module | PD.2 | FALSE
PD | PD.7 | Outcome Drawer [Send] → live | Replace disabled [Send] button with live handler that calls adapter.sendEmail(). Show preview first until engine cover-notes are trusted, then fire-and-forget. | Closes the loop from engine decision → operator approval → actual send | Component | OutcomeDrawer.tsx | PD.2, E.6 | FALSE
PD | PD.8 | Webhook handlers — inbound events | email.opened / email.replied / activity.completed / deal.stage_changed → feed into engine as evidence | Engine uses email opens as evidence when re-scoring signals; manual deal-stage moves trigger belief re-scoring | Routes + Service | new route + adapter inbound path | PD.2, PD.4 | FALSE
ADR | ADR.1 | ADR 001 — Tag/outcome/side-effect model | Three-layer canonical model with allowed-combinations matrix. 8 outcomes × 9 side-effects. Configurable max_call_attempts + cool_off_days (global + per-tag). | Locks in tag semantics so future operators and devs share one mental model | Doc | docs/decisions/001-tag-outcome-side-effect-model.md | None | TRUE
ADR | ADR.2 | ADR 002 — Pipedrive integration architecture | App = brain, Pipedrive = execution substrate. Per-field sync direction. Idempotency via stored IDs. Dead-letter queue. Rate limiting. Disable Aircall native. | Avoids later rework when Phase 8 starts; unambiguous about what goes where. | Doc | docs/decisions/002-pipedrive-integration.md | None | TRUE
ADR | ADR.3 | ADR 003 — Engine phase plan | Eight-phase rollout: 1-3 shipped (engine core, persistence, webhook wiring); 4 (Outcome Drawer) shipped; 4.5 V3 upgrade, 4.6 drawer extension, 5 pre-call panel, 6 V1 retirement, 7 update mechanism, 8 Pipedrive. | Phased delivery keeps each piece testable; Phase 4.5/4.6 inserted post-V3 spec drop | Doc | docs/decisions/003-engine-phase-plan.md | None | TRUE | Needs update to reflect new 4.5/4.6

## Sheet3
Here are the updated Phase 1 tasks (1.3-1.5 changed, rest stays):
Phase | Ref | Task Name | What Changes | Why | Type | Files Affected | Dependencies | Status | Notes
1 | 1.3 | Aircall API client (contacts) | Create lib/integrations/aircall/client.ts: createContact(firstName, lastName, phone, email), getContact(id), listUsers(). Create contact in Aircall when queued for calling, store aircall_contact_id on contact record. No power dialer functions. | Need contacts to exist in Aircall before calling so webhook events match back. Click-to-call replaces power dialer — simpler, caller controls pace. | Integration | lib/integrations/aircall/src/client.ts | 2.0a | Not Started | Rate limit: 60 req/min. Contact created on queue, not on upload.
1 | 1.4 | Campaign config + local queue service | Campaigns: name, filter criteria on local contact pool, daily_quota, assigned agent. Queue service: query contacts matching criteria, exclude dispatched/cool-off/no-interest, mark as queued with dispatch_date, create contact in Aircall if aircall_contact_id is null. Start-of-day reconciliation: queued contacts with no call record from yesterday reset to pool. No Aircall power dialer — queue is managed locally. | Daily call queue managed in our app. Contacts pushed to Aircall on queue so they exist for matching. Caller uses click-to-call from our UI. | Service + Schema | lib/db/src/schema/campaign-config.ts, lib/dispatchService.ts, routes/campaigns/index.ts | 1.1, 1.3 | Not Started | Local queue replaces Aircall power dialer.
1 | 1.5 | Campaign Config + Call Queue page | Campaign config: create/edit campaigns, filter criteria on local pool, assign agent, set daily quota. Call Queue view: today's prioritised list (callbacks, interested, retries, fresh). Each row shows contact name, company, phone, last outcome, call attempts. Click-to-call button per row (triggers aircall:// protocol or embedded widget). Fill Queue button with breakdown. Embedded Aircall phone widget in side panel for side-by-side calling. | Caller opens one page each morning, sees their queue, clicks Call — Aircall opens alongside lead context. No app switching. Tags and notes captured in Aircall widget, flow back via webhooks. | Frontend | pages/campaign-config.tsx, pages/call-queue.tsx, components/aircall-widget.tsx, components/layout.tsx, App.tsx | 1.4, 2.0a | Not Started | Aircall Phone SDK embedded widget. Click-to-call for outbound.
And one new task to add:
Phase | Ref | Task Name | What Changes | Why | Type | Files Affected | Dependencies | Status | Notes
1 | 1.7 | Aircall embedded phone widget | Integrate Aircall Phone SDK as embeddable widget. Side panel component that can be toggled open/closed. Supports make/receive calls, tagging, notes, after-call work — all within our app. Widget state syncs with current contact being viewed. | Eliminates app switching between Aircall and Content Unlocker. Caller sees belief map and context while on the call. Tags captured in widget flow back via webhooks. | Frontend + Integration | components/aircall-widget.tsx, pages/call-queue.tsx, pages/call-prep.tsx | 2.0a | Not Started | Requires Aircall Phone SDK. Research embed options.

## New Files
File Path | Phase | Type | Purpose | Dependencies
lib/db/src/schema/lead-conversations.ts | 0 | Schema | Generic conversations table for all transcript sources | None
artifacts/api-server/src/lib/intelligenceService.ts | 0 | Service | Claude intelligence generation with progressive merge | None
artifacts/api-server/src/lib/beliefAnalysisService.ts | 0 | Service | Claude belief analysis with state preservation | None
artifacts/api-server/src/lib/analysisPipeline.ts | 0 | Service | Orchestrates: save transcript -> intelligence -> beliefs -> summary | intelligenceService, beliefAnalysisService
lib/db/src/schema/pipedrive-sync.ts | 1 | Schema | Pipedrive sync configuration and field mapping | None
lib/db/src/schema/pipedrive-persons.ts | 1 | Schema | Cache of Pipedrive person data with lead FK | None
lib/integrations/pipedrive/src/client.ts | 1 | Integration | Thin fetch wrapper for Pipedrive REST API | None
artifacts/api-server/src/lib/pipedriveSyncService.ts | 1 | Service | Full sync, incremental sync, write-back to Pipedrive | pipedrive client, fuzzyMatch
artifacts/api-server/src/routes/pipedrive/index.ts | 1 | Routes | Sync trigger, webhook receiver, person browsing, link/queue | pipedriveSyncService
artifacts/unlock-intel/src/pages/contact-pool.tsx | 1 | Page | Browse Pipedrive contacts, filter, bulk queue for outreach | Pipedrive routes
artifacts/api-server/src/lib/aircallTranscriptUtils.ts | 2 | Utility | Extracted Aircall format detection and normalization | None
artifacts/api-server/src/lib/transcriptionService.ts | 2 | Service | AI Assist or external Whisper/Deepgram transcription | None
artifacts/api-server/src/lib/callOutcomeService.ts | 2 | Service | Tag-to-action mapping with TAG_MAPPING config | lead_conversations schema
artifacts/api-server/src/lib/calendarService.ts | 2 | Service | Create meeting/callback/follow-up calendar events | google-calendar client
lib/integrations/google-calendar/src/client.ts | 2 | Integration | Google Calendar API with OAuth (direct, not Replit) | None
artifacts/api-server/src/routes/aircall/index.ts | 2 | Routes | Webhook handler for call.ended, call.tagged, transcription.created | transcriptionService, callOutcomeService
artifacts/api-server/src/routes/fireflies/index.ts | 2 | Routes | Webhook handler for Fireflies transcription events | analysisPipeline
artifacts/unlock-intel/src/pages/call-inbox.tsx | 2 | Page | All conversations with status, filters, manual link, reprocess | Aircall + Fireflies routes
lib/db/src/schema/pipeline-jobs.ts | 3 | Schema | Job queue with batch_id, status, attempts, timestamps | None
artifacts/api-server/src/lib/pipelineQueue.ts | 3 | Service | Queue processor with orphan recovery and heartbeat | pipeline-jobs schema, batchProcess utility
artifacts/api-server/src/routes/pipeline/index.ts | 3 | Routes | Enqueue, status, job list, retry, cancel | pipelineQueue
artifacts/unlock-intel/src/pages/call-queue.tsx | 4 | Page | Daily prioritised call list with belief completion | call outcome fields, lead_conversations
artifacts/unlock-intel/src/pages/belief-admin.tsx | 4 | Page | Belief registry editor, doc-belief matrix, gate rules | belief_registry schema
lib/db/src/schema/contacts.ts | CL | Schema | Contacts pool with dispatch_status / dispatch_date / call_attempts / last_call_outcome / callback_date / cool_off_until | None
lib/db/src/schema/call-list-config.ts | CL | Schema | Call list named configs with daily quota, agent assignment, filter criteria | contacts
lib/db/src/schema/call-list-memberships.ts | CL | Schema | Append-only bridging table with carried_from_id chain + partial unique index on active membership | contacts, call-list-config
artifacts/api-server/src/lib/dispatchService.ts | CL | Service | fillQueue + getQueueStatus + getCallList + reconcileUncalledContacts | All schemas above
artifacts/api-server/src/routes/campaigns-dispatch/index.ts | CL | Routes | Call list CRUD + queue actions + carry-over with target_call_list_id | dispatchService
artifacts/unlock-intel/src/pages/call-command.tsx | CL | Page | Operator's daily dialing UI (current contact, Up Next, queue stats, Aircall widget integration, SSE subscription) | campaigns-dispatch routes, useAircallPhone hook
lib/db/src/schema/agents.ts | AC | Schema | Operators with aircall_user_id linkage | None
artifacts/api-server/src/lib/tagModel.ts | AC | Service | Canonical outcomes/side-effects/allowed-combinations matrix + cool-off helpers | None
artifacts/api-server/src/routes/aircall/index.ts | AC | Routes | Webhook handler: call.ended, call.tagged (single mutation point in db.transaction), call.commented, transcription.created, summary.created. Untagged-conversation sweep. | tagModel, agents, contacts, call-list-memberships
artifacts/api-server/src/lib/queueEvents.ts | AC | Service | SSE broadcaster — subscribers set + notifyQueueChanged + keepalive | None
artifacts/api-server/src/routes/events/index.ts | AC | Routes | /events/queue SSE endpoint + /events/health diagnostic | queueEvents
artifacts/api-server/src/engine/v2/version.ts | E | Engine | ENGINE_VERSION constant + spec link | None
artifacts/api-server/src/engine/v2/types.ts | E | Engine | All TypeScript types — SignalDef, Investor, EngineOutput, etc. | None
artifacts/api-server/src/engine/v2/config.ts | E | Engine | PART A — typed constants for SIGNAL_REGISTRY, GATES, ROUTING_MAP, PERSONA_CONFIG, COMPLIANCE, etc. | types
artifacts/api-server/src/engine/v2/util.ts | E | Engine | Shared helpers (countOccurrences, isSignalActive, nowIso) | types
artifacts/api-server/src/engine/v2/functions/*.ts | E | Engine | C1-C10 pure functions: detectPersona, detectHotButton, analyseSignals, evaluateGates, routeContent, generateCoverNote, determineNextAction, buildCrmNote, validateCompliance, processTranscript | config + types + util
artifacts/api-server/src/engine/v2/persistence.ts | E | Service | loadInvestor + saveEngineRun + read helpers; bridges DB ↔ engine types; sets callback_date from NBA.timing | engine_* schemas + engine module
artifacts/api-server/src/engine/v2/index.ts | E | Engine | Public re-exports | All of the above
artifacts/api-server/src/engine/v2/tests/runTests.ts | E | Tests | Runnable harness with 16 fixtures (D1-D5) | engine module
lib/db/src/schema/engine-investor-state.ts | E | Schema | Per-contact persona, hot button, demo score, fact find | contacts
lib/db/src/schema/engine-signals.ts | E | Schema | Current signal state per (contact, code) with partial unique idx | contacts
lib/db/src/schema/engine-signal-transitions.ts | E | Schema | Append-only audit log of state changes | contacts
lib/db/src/schema/engine-runs.ts | E | Schema | Full EngineOutput JSON per invocation | contacts, lead-conversations
lib/db/src/schema/engine-artifacts-sent.ts | E | Schema | Documents dispatched (will populate when send wired) | contacts
artifacts/api-server/src/routes/engine/index.ts | E | Routes | /engine/version, /engine/contact/:id, /engine/runs/:id, POST /engine/reprocess | engine module + persistence
artifacts/unlock-intel/src/components/OutcomeDrawer.tsx | E | Component | Right-side post-call drawer showing engine output, NBA card, signal changes, gates, flags | engine routes
docs/decisions/README.md + 001/002/003.md | ADR | Doc | Architecture Decision Records — tag model, Pipedrive integration, engine phase plan | None
docs/402_SPEC_Intelligence_Engine_V2_CURRENT.md | E | Doc | Engine V2 spec (Part A config, Part B types, Part C functions, Part D fixtures, Part E versioning) | None
docs/402_SPEC_Intelligence_Engine_V3_CURRENT.md | E | Doc | Engine V3 spec — adds A10-A17 + C11-C16 + EngineOutputV3 | V2 spec
docs/unlock_database_erd.jsx | Doc | Doc | Interactive React ERD for the database schema | None
docs/CallList_Refactor_Test_Cases.xlsx | CL | Doc | Manual test cases for call-list refactor (10 tests, summary tab) | None

## Modified Files
File Path | Phase(s) | Change Description
lib/db/src/schema/leads.ts | 0, 1 | Add email, phone, call_attempts, last_call_outcome, callback_date, outreach_paused_until, batch_date, campaign_name, sequence_stage, pipedrive_person_id
lib/db/src/schema/belief-registry.ts | 0 | Add conversation_question, content_if_unresolved, red_flag_signals, green_flag_signals
lib/db/src/schema/index.ts | 0-3 | Export new schema tables (lead_conversations, pipedrive-*, pipeline-jobs)
artifacts/api-server/src/routes/recommendation/index.ts | 0 | Save transcript_text to lead after analysis, trigger pipeline in background
artifacts/api-server/src/routes/lead-intelligence/index.ts | 0 | Thin wrapper calling intelligenceService (merge-not-overwrite)
artifacts/api-server/src/routes/lead-beliefs/index.ts | 0 | Thin wrapper calling beliefAnalysisService (preserve established)
artifacts/api-server/src/routes/leads/index.ts | 0, 4 | Add pagination + call-queue endpoint + call-prep endpoint
artifacts/api-server/src/routes/content/feature-update.ts | 0 | Fix dry_run: skip DB writes when dry_run is true
artifacts/api-server/src/routes/index.ts | 1-3 | Register pipedrive, aircall, fireflies, pipeline route files
artifacts/api-server/src/lib/dataManager.ts | 0 | Seed conversation_question and content_if_unresolved for all 16+ beliefs
artifacts/unlock-intel/src/pages/leads.tsx | 0, 3 | Server-side pagination + bulk Run Pipeline action
artifacts/unlock-intel/src/pages/lead-detail.tsx | 2, 4 | Log Meeting button, conversations section, belief diffs, timeline
artifacts/unlock-intel/src/pages/call-prep.tsx | 4 | Complete redesign: qualification gates, belief map, context, Schedule Follow-up
artifacts/unlock-intel/src/pages/dashboard.tsx | 4 | Add funnel view, wave tracking, error visibility, belief progress widgets
artifacts/unlock-intel/src/components/layout.tsx | 1-4 | Add nav items: Contact Pool, Call Inbox, Call Queue, Belief Admin
artifacts/unlock-intel/src/App.tsx | 1-4 | Add routes for new pages
lib/api-spec/openapi.yaml | 0-4 | New endpoints and schemas for all phases
lib/db/src/schema/contacts.ts | CL refactor | Removed campaign_name (replaced by call_list_memberships bridging table)
lib/db/src/schema/lead-conversations.ts | E.3 | Added engine_version column for attribution
artifacts/api-server/src/index.ts | AC.6 | Boots untagged-conversation sweep on startup
artifacts/api-server/src/routes/index.ts | AC.7, E.3 | Mounts engineRouter and eventsRouter
artifacts/api-server/src/routes/settings/index.ts | AC.8, AC.9 | Defends against masked-token overwrite; surfaces Aircall API errors with hints
artifacts/unlock-intel/src/pages/settings.tsx | AC.2-AC.4, AC.8-9 | Tag mapping editor with dependent dropdowns; max_call_attempts + cool_off_days inputs; per-tag cool_off_days override; password-field handling fixed
artifacts/unlock-intel/src/pages/call-command.tsx | CL, AC.7, E.4 | SSE subscription, cursor re-alignment by contact ID, manual Refresh button, Up Next swap-on-click, OutcomeDrawer integration, Aircall dialing widget hook

## Environment Variables
Variable Name | Phase | Purpose | Required
PIPEDRIVE_API_TOKEN | 1 | Pipedrive API authentication | Required
PIPEDRIVE_COMPANY_DOMAIN | 1 | Pipedrive subdomain for API URL | Required
AIRCALL_WEBHOOK_TOKEN | 2 | Aircall webhook signature verification | Required
AIRCALL_API_ID | 2 | Aircall API authentication (for fetching transcripts) | Required
AIRCALL_API_TOKEN | 2 | Aircall API authentication | Required
AIRCALL_TRANSCRIPTION_MODE | 2 | ai_assist or external (determines transcript source) | Required
TRANSCRIPTION_API_KEY | 2 | Whisper/Deepgram API key | Optional (external mode only)
FIREFLIES_WEBHOOK_SECRET | 2 | Fireflies webhook signature verification | Required
GOOGLE_CALENDAR_CLIENT_ID | 2 | Google Calendar OAuth client ID | Required
GOOGLE_CALENDAR_CLIENT_SECRET | 2 | Google Calendar OAuth client secret | Required
GOOGLE_CALENDAR_REDIRECT_URI | 2 | Google Calendar OAuth callback URL | Required

## Phase Summary
Phase | Name | Goal | Tasks | New Files | Key Deliverable
0 | Fix Data Flow + Progressive Intelligence | Fix broken plumbing, make intelligence accumulate, prepare schema for integrations | 11 | 4 | Analysis pipeline that auto-triggers and preserves intelligence across conversations
1 | Pipedrive Integration | Sync 25K+ contacts, browse full pool, select and dispatch for outreach | 5 | 6 | Contact Pool page with bulk Queue for Outreach
2 | Aircall + Fireflies + Calendar | Receive call outcomes and transcripts automatically, create calendar events | 10 | 8 | Operational loop closes: call -> outcome -> action -> next call
3 | Batch Processing at Scale | Handle hundreds of leads per day without timeouts or rate limits | 3 | 3 | Queue with orphan recovery processing at scale
4 | Belief-Driven Call Prep + Visibility | Make the tool something you open every morning. Belief map as primary interface. | 9 | 2 | Call prep page, daily queue, dashboard, belief admin
S | Suggestions (Post-Core) | Elevate from functional to genuinely powerful intelligence tool | 7 | 0 | Discovery scoring, belief analytics, content effectiveness, lead scoring
CL | Call List Infrastructure | Pool, dispatch, memberships, queue UI | 7 | 6 | Operator-facing Call Command page driving day-to-day dialing
AC | Aircall Integration | Webhook handler, canonical tag model, single-mutation refactor, SSE, settings UI | 9 | 4 | End-to-end call flow: ring → tag → outcome → recall/cool-off without races
E1-3 | Engine V2 Core (shipped) | Pure module + persistence + transcript wiring + inspection endpoints | 3 | 17 | processTranscript runs on every transcript; investor profile accumulates
E4 | Engine V2 — Outcome Drawer (shipped) | Right-side drawer auto-opens after call; shows persona, signal changes, NBA, gates, flags | 1 | 1 | Operator sees engine recommendation immediately after each call
E4.5 | Engine V3 upgrade (planned) | Add A10-A17 config sections + C11-C16 functions + EngineOutputV3 | 1 | 0 | Question detection, demo segment analysis, email generation, post-close + Book 2 routing
E4.6 | Outcome Drawer V3 (planned) | Show questions detected, demo segments, email draft, post-close checklist | 1 | 0 | V3 engine output surfaced in operator UI
E5 | Pre-call Panel (planned) | Replace empty Call Prep card with persona, hot button, prior-call summary, V3 question prompts | 1 | 1 | Operator briefed before dialing
E6 | V1 retirement (planned) | Migrate lead_beliefs → engine_signals; deprecate old services | 1 | 0 | Single intelligence system
E7 | Engine update mechanism (planned) | Admin page + spec-update workflow | 1 | 1 | Future spec drops are mechanical
PD | Pipedrive Integration (planned — Phase 8) | Adapter, document registry, dead-letter queue, audit log, rate limiter, headless send, inbound webhook handlers | 8 | 5 | App is brain, Pipedrive is execution substrate; closed loop on email opens/replies
ADR | Architectural Decision Records (shipped) | ADR 001 tag model, ADR 002 Pipedrive integration, ADR 003 phase plan | 3 | 4 | Team-visible rationale checked into repo at docs/decisions/