## Implementation Tracker
Phase | Ref | Task Name | What Changes | Why | Type | Files Affected | Dependencies | Status | Notes
0 | 0.1 | Save transcript to lead | After Claude analysis, write transcript_text to lead record if lead_id known | Transcripts are lost after analysis. No history for progressive intelligence. | Fix | routes/recommendation/index.ts | None | Not Started
0 | 0.2 | Extract service functions | Create intelligenceService.ts, beliefAnalysisService.ts, analysisPipeline.ts. Refactor route handlers to thin wrappers. | Logic trapped in route handlers can't be called from webhooks, queue, or other routes. | Service | lib/intelligenceService.ts, lib/beliefAnalysisService.ts, lib/analysisPipeline.ts, routes/lead-intelligence, routes/lead-beliefs | None | Not Started
0 | 0.3 | Intelligence: merge not overwrite | Pass existing intelligence profile as context to Claude. Add preserve/merge instructions. | Each call overwrites previous profile. Hot button from call 1 wiped by call 2. | Service | lib/intelligenceService.ts | 0.2 | Not Started
0 | 0.4 | Belief analysis: preserve established | Pass existing belief states as context. ESTABLISHED stays unless explicit reversal. | Beliefs established in call 1 reset to UNKNOWN in call 2 because not discussed. | Service | lib/beliefAnalysisService.ts | 0.2 | Not Started
0 | 0.5 | Auto-trigger pipeline | After /recommendation/analyze, fire runPostTranscriptPipeline() in background if lead_id provided. | Users must manually click Generate Profile then Analyze Beliefs. 3 clicks instead of 0. | Service | routes/recommendation/index.ts, lib/analysisPipeline.ts | 0.1, 0.2 | Not Started
0 | 0.6 | Fix feature-update dry_run | Add conditional skip of DB writes when dry_run: true. | dry_run parameter accepted but ignored. Testing corrupts document review states. | Fix | routes/content/feature-update.ts | None | Done | Was already implemented correctly in code
0 | 0.7 | Server-side pagination | Add page/page_size params, LIMIT/OFFSET, COUNT(*). Frontend page controls + debounced search. | GET /leads returns all leads. Won't work with 25K+. | Route + Frontend | routes/leads/index.ts, pages/leads.tsx, openapi.yaml, api-zod | None | In Progress | Backend code done, frontend compatibility fix applied. Build/bundle issue under investigation.
0 | 0.8 | Schema: leads table additions | Add email, phone, call_attempts, last_call_outcome, callback_date, outreach_paused_until, batch_date, campaign_name, sequence_stage, pipedrive_person_id | Pipedrive sync, Aircall matching, and call outcome logic all need these fields. | Schema | lib/db/src/schema/leads.ts | None | Done | Schema pushed, columns verified in DB
0 | 0.9 | Schema: belief registry questions | Add conversation_question, content_if_unresolved, red_flag_signals, green_flag_signals. Seed data for all 16+ beliefs. | Call prep page needs to show what question to ask per belief and what content to send. | Schema + Config | lib/db/src/schema/belief-registry.ts, dataManager.ts | None | Done | Schema pushed, seed data migrated via SQL script
0 | 0.10 | Schema: lead_conversations table | Generic conversations table replacing Aircall-specific. Source field (aircall/fireflies/manual). beliefs_before/after snapshots, intelligence_delta. | Transcripts come from multiple sources. Pipeline doesn't care about source. | Schema | lib/db/src/schema/lead-conversations.ts, lib/db/src/schema/index.ts | None | Done | Schema pushed, table verified in DB
0 | 0.11 | Conversation summary generation | After analysis, Claude generates 3-5 sentence summary. Future analyses receive summaries as context. | Progressive intelligence needs summaries. Full transcripts won't fit in context. | Service | lib/analysisPipeline.ts | 0.2, 0.10 | Not Started
1 | 1.1 | Pipedrive: database schema | Create pipedrive_sync_config and pipedrive_persons tables. | Need tables to store synced contacts and sync configuration. | Schema | lib/db/src/schema/pipedrive-sync.ts, lib/db/src/schema/pipedrive-persons.ts | 0.8 | Not Started
1 | 1.2 | Pipedrive: API client | Create lib/integrations/pipedrive/ package with thin fetch wrapper. | Need a client to call Pipedrive REST API. | Integration | lib/integrations/pipedrive/src/client.ts, lib/integrations/pipedrive/package.json | None | Not Started | Env: PIPEDRIVE_API_TOKEN, PIPEDRIVE_COMPANY_DOMAIN
1 | 1.3 | Pipedrive: sync service | Create pipedriveSyncService with runFullSync, syncSinglePerson, pushFieldToPipedrive. Custom field mapping (Batch Date, Campaign Name, etc). | Need to sync 25K+ contacts with bidirectional field mapping. | Service | lib/pipedriveSyncService.ts | 1.1, 1.2 | Not Started | Field mapping in DB, not code
1 | 1.4 | Pipedrive: API routes | POST /pipedrive/sync, GET /status, POST /webhook, GET /persons, POST /link, POST /queue-outreach | Frontend and webhooks need endpoints to trigger sync and browse contacts. | Route | routes/pipedrive/index.ts, routes/index.ts | 1.3 | Not Started
1 | 1.5 | Pipedrive: Contact Pool page | New page with paginated table, search, filters, bulk Queue for Outreach, Link to Lead, sync banner. | Team needs to browse the full Pipedrive pool and select contacts for outreach. | Frontend | pages/contact-pool.tsx, components/layout.tsx, App.tsx | 1.4 | Not Started
1 | 1.6 | Pipedrive push service | One-way push on interested/meeting-booked. Create person + deal in Pipedrive. Store IDs on contact record. No sync, no cache. | Only qualified leads enter Pipedrive. Keeps it clean. | Service | lib/pipedrivePushService.ts, routes/pipedrive/index.ts | 1.1 | Not Started | v6: NEW. Simple one-way push.
2 | 2.1 | Aircall: design constraints (research) | Document Aircall API behavior: no transcript in call.ended, tags arrive late, transcription needs AI Assist. | Must understand API before building. Wrong assumptions = broken integration. | Config | N/A (documented in plan) | None | Not Started | Research complete
2 | 2.2 | Aircall: transcription service | Two paths: AI Assist (webhook) or external (download MP3 + Whisper/Deepgram). Config-driven. | call.ended has no transcript. Must handle transcription separately. | Service | lib/transcriptionService.ts | 0.10 | Not Started | Env: AIRCALL_TRANSCRIPTION_MODE, TRANSCRIPTION_API_KEY
2 | 2.3 | Aircall: extract transcript utils | Move isAircallFormat, normaliseAircallTranscript, identifyAgentLabel to shared utility. | These functions are embedded in recommendation route. Need them in webhook handler too. | Utility | lib/aircallTranscriptUtils.ts, routes/recommendation/index.ts | None | Not Started
2 | 2.4 | Aircall: call outcome service | Map tags to actions. TAG_MAPPING config object. interested/no-interest/meeting-booked/no-answer/callback/not-now. | Without outcomes, leads stay in same state regardless of call result. Loop doesn't close. | Service | lib/callOutcomeService.ts | 0.8, 0.10 | Not Started | v6: interested/meeting-booked also trigger Pipedrive push (1.6)
2 | 2.5 | Aircall: webhook handler | POST /aircall/webhook handling call.ended, call.tagged, transcription.created events. | Need to receive Aircall events automatically instead of manual file upload. | Route | routes/aircall/index.ts, routes/index.ts | 2.2, 2.3, 2.4 | Not Started | v6: Outcomes reference local contacts table
2 | 2.6 | Fireflies: webhook handler | POST /fireflies/webhook. Match by participant email. Create lead_conversations, trigger pipeline. | Google Meet transcripts must flow automatically. Manual paste = inconsistent logging. | Route | routes/fireflies/index.ts, routes/index.ts | 0.10, 0.5 | Not Started | Env: FIREFLIES_WEBHOOK_SECRET
2 | 2.7a | Google Calendar: API client | Create lib/integrations/google-calendar/ with OAuth flow, event CRUD, date range queries. | Need Calendar API access for meeting and callback invites. | Integration | lib/integrations/google-calendar/src/client.ts | None | Not Started | Env: GOOGLE_CALENDAR_CLIENT_ID/SECRET/REDIRECT
2 | 2.7b | Google Calendar: calendar service | createMeetingEvent, createCallbackEvent, createFollowUpEvent, getEventsForDate. | Outcome dialog needs to auto-create calendar events for meetings and callbacks. | Service | lib/calendarService.ts | 2.7a | Not Started
2 | 2.7c | Google Calendar: outcome dialog | Add date/time picker to outcome dialog. Auto-create calendar event for meeting-booked and callback-requested. | Investors need calendar invites. No invite = nothing in their diary. | Frontend | pages/call-prep.tsx, pages/call-inbox.tsx | 2.7b, 2.4 | Not Started
2 | 2.8a | Frontend: Call Inbox page | New page listing all conversations. Source icons, status indicators, filters, manual link, reprocess. | Need visibility of all calls/meetings across sources with status tracking. | Frontend | pages/call-inbox.tsx, components/layout.tsx, App.tsx | 2.5, 2.6 | Not Started
2 | 2.8b | Frontend: Lead detail updates | Add Log Meeting button, Conversations section with summaries, belief diffs, intelligence delta. | Lead detail needs conversation history and what-changed views. | Frontend | pages/lead-detail.tsx | 0.10, 0.11 | Not Started
3 | 3.1 | Pipeline: job tracking schema | pipeline_jobs table with batch_id, job_type, status, lead_id, attempts, timestamps. | Need persistent job tracking for batch processing. | Schema | lib/db/src/schema/pipeline-jobs.ts | None | Not Started
3 | 3.2 | Pipeline: queue service + orphan recovery | pipelineQueue.ts using batchProcess utility. Startup recovery, 60s polling, heartbeat. | Replit may kill processes mid-batch. Must detect and recover orphaned jobs. | Service | lib/pipelineQueue.ts | 3.1, 0.2 | Not Started
3 | 3.3 | Pipeline: API routes + frontend | POST /enqueue, GET /status, GET /jobs. Bulk Run Pipeline actions on leads + contact pool. Progress banner. | Need to enqueue hundreds of leads and track progress. | Route + Frontend | routes/pipeline/index.ts, pages/leads.tsx, pages/contact-pool.tsx | 3.2, 0.7 | Not Started
4 | 4.1 | Belief-driven call prep page | Complete redesign: qualification gates, belief map with questions, context (summaries, sent docs, objections), action buttons. | Caller needs belief map as primary interface before every call. Current page is generic 4 questions. | Frontend | pages/call-prep.tsx, routes/leads/index.ts (call-prep endpoint) | 0.9, 0.10, 0.11 | Not Started | THE primary interface
4 | 4.2 | Daily call queue page | New page: prioritised list (callbacks, interested, cold at sequence day, re-entries). Re-entry reset at query time. | Caller needs to know who to call each morning. Currently no prioritised list. | Frontend + Route | pages/call-queue.tsx, routes/leads/index.ts (call-queue endpoint) | 2.4, 0.8 | Not Started | Re-entry flips paused->active at query time
4 | 4.3 | Dashboard: campaign wave tracking | Widget showing active wave, dispatched today/week, total in wave, remaining in pool. | Team needs to see where they are in the 25K campaign. | Frontend + Route | pages/dashboard.tsx, routes/dashboard/index.ts | 0.8 | Not Started
4 | 4.4 | Dashboard: funnel view | Counts by pipeline_stage. Plus terminal states (Closed, Paused, Passive). | Need 'where is everyone right now' at a glance. | Frontend + Route | pages/dashboard.tsx, routes/dashboard/index.ts | 0.8 | Not Started
4 | 4.5 | Dashboard: error visibility | 'X items need attention' widget. Failed jobs, syncs, unmatched calls, unprocessed outcomes. | Silent failures where leads fall through cracks is worst outcome. | Frontend + Route | pages/dashboard.tsx, routes/dashboard/index.ts | 2.5, 3.1 | Not Started
4 | 4.6 | Enhanced lead detail timeline | Unified timeline: stage changes, conversations, sends, belief transitions, intelligence updates. | Need complete chronological interaction history per lead. | Frontend | pages/lead-detail.tsx | 0.10, 2.4 | Not Started
4 | 4.7 | Content routing audit | Review recommendation route. Ensure belief gates are primary driver, stage is sanity check only. | Stage currently filters content alongside beliefs. Beliefs should be primary. | Review + Fix | routes/recommendation/index.ts | None | Not Started | Review task, not rewrite
4 | 4.8 | Belief system admin page | New page: belief registry editor, document-to-belief matrix, gate rules overview. | Non-developers can't adjust beliefs, questions, gates, or content mappings without code. | Frontend | pages/belief-admin.tsx, components/layout.tsx, App.tsx | 0.9 | Not Started
4 | 4.9 | Content handoff | Copy to Clipboard for AC paste. Better send history UI. Outreach queue page (optional). | Content goes to AC manually. Need smooth copy flow. | Frontend | pages/lead-detail.tsx, pages/recommend.tsx | None | Not Started | Outreach queue deferred unless >50/day
S | S1 | Discovery completeness score | Score each conversation 0-100% on new intelligence gathered. Aggregate per agent. | See which callers do real discovery vs going through motions. | Service + Frontend | lib/analysisPipeline.ts, pages/call-inbox.tsx | 0.2, 0.11 | Not Started | Post-core
S | S2 | Belief journey analytics | Dashboard: hardest beliefs, avg conversations per belief, distribution by cluster. | Identify systematic weaknesses in scripts or content. | Frontend + Route | pages/dashboard.tsx or new analytics page | 0.10 | Not Started | Post-core
S | S3 | Content effectiveness tracking | Link doc sends to subsequent belief state changes. Build effectiveness map. | Data-driven content strategy. Rewrite underperforming documents. | Service + Frontend | lib/analysisPipeline.ts, pages/dashboard.tsx | 0.10, 0.11 | Not Started | Post-core
S | S4 | Objection memory | Track objections across conversations with resolution status. Show in call prep. | Callers don't re-raise resolved objections. Surface recurring issues. | Schema + Service | lib/db schema changes, lib/analysisPipeline.ts, pages/call-prep.tsx | 0.10, 4.1 | Not Started | Post-core
S | S5 | Smart next action engine | Multi-step: conversational goal + content + gate check + escalation trigger. | From 'what to send' to 'what to do next and why'. | Service | routes/leads/index.ts, lib/analysisPipeline.ts | 0.9, 4.1 | Not Started | Post-core
S | S6 | Pre-call briefing card | Claude auto-generates 30-second context briefing per lead. Cached, regenerated after each call. | Perfect context in 30 seconds before every call. | Service + Frontend | routes/leads/index.ts, pages/call-prep.tsx | 0.2, 0.11, 4.1 | Not Started | Post-core
S | S7 | Belief-based lead scoring | Score based on qualification gates, universal/cluster/founding beliefs. Formula-driven. | Prioritise genuinely ready leads over email openers. | Service + Frontend | routes/leads/index.ts, pages/leads.tsx, pages/call-queue.tsx | 0.9 | Not Started | Post-core

## New Files
File Path | Phase | Type | Purpose | Dependencies
lib/db/src/schema/lead-conversations.ts | 0 | Schema | Generic conversations table for all transcript sources | None
artifacts/api-server/src/lib/intelligenceService.ts | 0 | Service | Claude intelligence generation with progressive merge | None
artifacts/api-server/src/lib/beliefAnalysisService.ts | 0 | Service | Claude belief analysis with state preservation | None
artifacts/api-server/src/lib/analysisPipeline.ts | 0 | Service | Orchestrates: save transcript -> intelligence -> beliefs -> summary | intelligenceService, beliefAnalysisService
lib/db/src/schema/pipedrive-sync.ts | 1 | Schema | Pipedrive sync configuration and field mapping | None
lib/db/src/schema/pipedrive-persons.ts | 1 | Schema | Cache of Pipedrive person data with lead FK | None
lib/integrations/pipedrive/src/client.ts | 1 | Integration | Thin fetch wrapper for Pipedrive REST API | None
artifacts/api-server/src/lib/pipedriveSyncService.ts | 1 | Service | Full sync, incremental sync, write-back to Pipedrive | pipedrive client, fuzzyMatch
artifacts/api-server/src/routes/pipedrive/index.ts | 1 | Routes | Sync trigger, webhook receiver, person browsing, link/queue | pipedriveSyncService
artifacts/unlock-intel/src/pages/contact-pool.tsx | 1 | Page | Browse Pipedrive contacts, filter, bulk queue for outreach | Pipedrive routes
artifacts/api-server/src/lib/aircallTranscriptUtils.ts | 2 | Utility | Extracted Aircall format detection and normalization | None
artifacts/api-server/src/lib/transcriptionService.ts | 2 | Service | AI Assist or external Whisper/Deepgram transcription | None
artifacts/api-server/src/lib/callOutcomeService.ts | 2 | Service | Tag-to-action mapping with TAG_MAPPING config | lead_conversations schema
artifacts/api-server/src/lib/calendarService.ts | 2 | Service | Create meeting/callback/follow-up calendar events | google-calendar client
lib/integrations/google-calendar/src/client.ts | 2 | Integration | Google Calendar API with OAuth (direct, not Replit) | None
artifacts/api-server/src/routes/aircall/index.ts | 2 | Routes | Webhook handler for call.ended, call.tagged, transcription.created | transcriptionService, callOutcomeService
artifacts/api-server/src/routes/fireflies/index.ts | 2 | Routes | Webhook handler for Fireflies transcription events | analysisPipeline
artifacts/unlock-intel/src/pages/call-inbox.tsx | 2 | Page | All conversations with status, filters, manual link, reprocess | Aircall + Fireflies routes
lib/db/src/schema/pipeline-jobs.ts | 3 | Schema | Job queue with batch_id, status, attempts, timestamps | None
artifacts/api-server/src/lib/pipelineQueue.ts | 3 | Service | Queue processor with orphan recovery and heartbeat | pipeline-jobs schema, batchProcess utility
artifacts/api-server/src/routes/pipeline/index.ts | 3 | Routes | Enqueue, status, job list, retry, cancel | pipelineQueue
artifacts/unlock-intel/src/pages/call-queue.tsx | 4 | Page | Daily prioritised call list with belief completion | call outcome fields, lead_conversations
artifacts/unlock-intel/src/pages/belief-admin.tsx | 4 | Page | Belief registry editor, doc-belief matrix, gate rules | belief_registry schema

## Modified Files
File Path | Phase(s) | Change Description
lib/db/src/schema/leads.ts | 0, 1 | Add email, phone, call_attempts, last_call_outcome, callback_date, outreach_paused_until, batch_date, campaign_name, sequence_stage, pipedrive_person_id
lib/db/src/schema/belief-registry.ts | 0 | Add conversation_question, content_if_unresolved, red_flag_signals, green_flag_signals
lib/db/src/schema/index.ts | 0-3 | Export new schema tables (lead_conversations, pipedrive-*, pipeline-jobs)
artifacts/api-server/src/routes/recommendation/index.ts | 0 | Save transcript_text to lead after analysis, trigger pipeline in background
artifacts/api-server/src/routes/lead-intelligence/index.ts | 0 | Thin wrapper calling intelligenceService (merge-not-overwrite)
artifacts/api-server/src/routes/lead-beliefs/index.ts | 0 | Thin wrapper calling beliefAnalysisService (preserve established)
artifacts/api-server/src/routes/leads/index.ts | 0, 4 | Add pagination + call-queue endpoint + call-prep endpoint
artifacts/api-server/src/routes/content/feature-update.ts | 0 | Fix dry_run: skip DB writes when dry_run is true
artifacts/api-server/src/routes/index.ts | 1-3 | Register pipedrive, aircall, fireflies, pipeline route files
artifacts/api-server/src/lib/dataManager.ts | 0 | Seed conversation_question and content_if_unresolved for all 16+ beliefs
artifacts/unlock-intel/src/pages/leads.tsx | 0, 3 | Server-side pagination + bulk Run Pipeline action
artifacts/unlock-intel/src/pages/lead-detail.tsx | 2, 4 | Log Meeting button, conversations section, belief diffs, timeline
artifacts/unlock-intel/src/pages/call-prep.tsx | 4 | Complete redesign: qualification gates, belief map, context, Schedule Follow-up
artifacts/unlock-intel/src/pages/dashboard.tsx | 4 | Add funnel view, wave tracking, error visibility, belief progress widgets
artifacts/unlock-intel/src/components/layout.tsx | 1-4 | Add nav items: Contact Pool, Call Inbox, Call Queue, Belief Admin
artifacts/unlock-intel/src/App.tsx | 1-4 | Add routes for new pages
lib/api-spec/openapi.yaml | 0-4 | New endpoints and schemas for all phases

## Environment Variables
Variable Name | Phase | Purpose | Required
PIPEDRIVE_API_TOKEN | 1 | Pipedrive API authentication | Required
PIPEDRIVE_COMPANY_DOMAIN | 1 | Pipedrive subdomain for API URL | Required
AIRCALL_WEBHOOK_TOKEN | 2 | Aircall webhook signature verification | Required
AIRCALL_API_ID | 2 | Aircall API authentication (for fetching transcripts) | Required
AIRCALL_API_TOKEN | 2 | Aircall API authentication | Required
AIRCALL_TRANSCRIPTION_MODE | 2 | ai_assist or external (determines transcript source) | Required
TRANSCRIPTION_API_KEY | 2 | Whisper/Deepgram API key | Optional (external mode only)
FIREFLIES_WEBHOOK_SECRET | 2 | Fireflies webhook signature verification | Required
GOOGLE_CALENDAR_CLIENT_ID | 2 | Google Calendar OAuth client ID | Required
GOOGLE_CALENDAR_CLIENT_SECRET | 2 | Google Calendar OAuth client secret | Required
GOOGLE_CALENDAR_REDIRECT_URI | 2 | Google Calendar OAuth callback URL | Required

## Phase Summary
Phase | Name | Goal | Tasks | New Files | Key Deliverable
0 | Fix Data Flow + Progressive Intelligence | Fix broken plumbing, make intelligence accumulate, prepare schema for integrations | 11 | 4 | Analysis pipeline that auto-triggers and preserves intelligence across conversations
1 | Pipedrive Integration | Sync 25K+ contacts, browse full pool, select and dispatch for outreach | 5 | 6 | Contact Pool page with bulk Queue for Outreach
2 | Aircall + Fireflies + Calendar | Receive call outcomes and transcripts automatically, create calendar events | 10 | 8 | Operational loop closes: call -> outcome -> action -> next call
3 | Batch Processing at Scale | Handle hundreds of leads per day without timeouts or rate limits | 3 | 3 | Queue with orphan recovery processing at scale
4 | Belief-Driven Call Prep + Visibility | Make the tool something you open every morning. Belief map as primary interface. | 9 | 2 | Call prep page, daily queue, dashboard, belief admin
S | Suggestions (Post-Core) | Elevate from functional to genuinely powerful intelligence tool | 7 | 0 | Discovery scoring, belief analytics, content effectiveness, lead scoring